Guidance for bilateral projects

August 2018

## Outline of the Identification Report

| Cover page | - Name and duration of the assignment - Type of report (draft / final draft / final) - Date and location - Authors of the report |
| --- | --- |
| Table of contents |  |
| Abbreviations |  |
| Summary | - An overview of country context, policies and development needs - An overview of the proposed project, scope, result areas and related output, proposed implementation modality - Brief summary of alternative scenarios or concepts, if available |
| 1. Background and Country Context | - Country context (using country strategy as a reference); short introduction of economy, development challenges, human rights situation - Sector context - Previous interventions or phases, if applicable - Short description of programme identification process (Max one paragraph), |
| 2. Policy Context | Policy Framework - Analyses of national policies and strategies relevant to the Project - Development needs, problems to be addressed and justification for the Project (e.g. reference to country's own development strategies and priorities that affect the initiative directly or indirectly) - Analysis of the sector policies, strategies and plans Institutional and financial framework - Relevant authorities and other organizations and actors and their main interventions in the sector, including all aid modalities in use - Financing: e.g. sector budget, share of national/ development partner funding, funding gaps - Coordination mechanisms at national/regional/local level Policy relevance - Rationale vis-à-vis Finnish policies, strategies, value-added and complementarity |
| 3. Description of the Proposed Project | 3.1. Overview of the Project - Rationale for launching the project and the proposed modality - Description of the internal project logic, Results Chain/ Theory of Change - Scope of the proposed project (e.g. duration, geographical scope etc.) 3.2. Results and key strategies - Description of results (outputs, outcome and impacts) expected to be achieved (based on the result chain or theory of change, including cross-cutting objectives relevant to the project) - Description of the key strategies to achieve the project results, main types of activities - Key milestones for project implementation - Defined outputs and main activities for the Inception Phase, including assumptions and preconditions for efficient start-up 3.3. Risk assessment and risk response - Summary of risks and risk responses (with reference to Risk Matrix to be annexed) |
| 4. Stakeholder analysis | - Stakeholder analysis and assessment; needs and opportunities: Who are the beneficiaries and stakeholders? Who are the Duty Bearers and Rights Holders? What are their responsibilities, rights and capacity gaps related to proposed intervention/ sector? |
| 5. Analysis of concept(s) | - Approach - What alternatives exist for the Finnish Support? I.e. the concept notes, what may they differ in (= results, implementation modalities, strategic choices)? What criteria are/ should be used for selection of the alternatives? - Analysis of potential modalities for project implementation; (pros and cons of options) - Analysis of scope of the implementation in terms of results and strategic choices. - Short presentation of alternative project concepts: a) b) Contemplation and comparison of various options (presented in Concept Notes) in accordance to the selected criteria, Concept note annexed to the Inception Report). |
| 6. Recommendations and Next Steps | - Critical issues and recommendations for decision-making and further planning |
| Annexes | - Concept note(s) for the proposed project - Background studies, documents consulted - Persons consulted - Relevant other background material such as statistics, maps, etc. |

Normally the Identification Report should not exceed 20 pages + annexes.